Overview
    Project Introduction and Objectives
    Current Level of Completion
Milestones and Deliverables
    Current Accomplishments
    Scheduled completions
    Missed Targets
Issues and Changes
    Open Issues
    Open Change Requests
Next Phase Schedule
    Start and completion targets
Summary
Project Overview Report: Research on Asynchronous Consensus Protocols
Project Introduction and Objectives:
This research introduces an academic exploration of current asynchronous consensus protocols with an objective of making a contribution in the field. To do this an fundamental understanding of the space needs to be established. This is done with an in-depth study of HoneyBadgerBFT and progressing to the BEAT protocol suite, then the Dumbo protocol suite, and finally culminating with the latest advancements being the Asynchronous Byzantine Fault Tolerant (ABFT) protocol. The overarching research objectives are as follows:
1. HoneyBadgerBFT Investigation:
  1. Examine the HoneyBadgerBFT protocol.
  2. Acquire understanding of its theoretical foundations.
  3. Evaluate its strengths and limitations.
  4. Solidify how its short comings were handled by the newer protocols.
2. BEAT Protocol Suite Exploration:
  1. Examine the BEAT protocol suite.
  1. Acquire understanding of its theoretical foundations.
  1. Evaluate its strengths and limitations.
  2. Solidify how its short comings were handled by ABFT and its trade offs with Dumbo.
Dumbo Protocol Suite Analysis:
  1. Examine the Dumbo protocol suite.
  2. Acquire understanding of its theoretical foundations.
  3. Evaluate its strengths and limitations.
  4. Solidify how its short comings were handled by ABFT and its trade offs with BEAT.
1. ABFT Protocol Research:
  1. Examine the Asynchronous Byzantine Fault Tolerant protocol.
  2. Understand how ABFT builds upon the collective knowledge of HoneyBadgerBFT, BEAT, and Dumbo protocols.
  3. Explore ABFT's innovative features, such as reduced computational overhead, enhanced performance, and superior scalability.
  4. Assess ABFT's practical applications and its suitability for decentralized distributed systems.
Current Level of Completion:
At the present stage of the project, the following key accomplishments and progress milestones have been achieved:
Current Accomplishments:
- Extensive literature review completed.
- Comprehensive understanding of HoneyBadgerBFT's theoretical foundation achieved.
Milestones and Deliverables:
The research project is organized into distinct phases, each with specific milestones and deliverables:
Scheduled Completions:
- Performance analysis and limitations study of HoneyBadgerBFT (Year 2).
- Investigation of optimization strategies and real-world viability of HoneyBadgerBFT (Year 3).
- Exploration of potential applications and preparation of the PhD Dissertation (Year 4).
Missed Targets: At this juncture, there are no significant missed targets or deviations from the planned project timeline.
Issues and Changes:
Open Issues: Currently, there are no open issues posing substantial hindrances to the research project's progression. However, ongoing vigilance will continue to identify and address emerging challenges.
Open Change Requests: The research project remains adaptable and open to adjustments in methodology, scope, or objectives as required by evolving findings or external factors.
Next Phase Schedule:
The research will progress to its next phase according to the following timeline:
- Year 2: Focused on the performance analysis and limitations study of HoneyBadgerBFT.
- Year 3: Dedicated to investigating optimization strategies and assessing real-world viability.
- Year 4: Devoted to exploring potential applications and preparing the PhD Dissertation.
Summary:
This comprehensive research project is dedicated to advancing the understanding of asynchronous consensus protocols. It embarks on a journey through HoneyBadgerBFT, the BEAT suite, Dumbo protocols, and culminates with the latest ABFT advancements. With a strong foundation in place, the project aims to provide valuable insights into decentralized distributed systems, their practical applications, and the evolving landscape of asynchronous consensus protocols. It remains flexible to accommodate emerging findings and aligns with its planned milestones and objectives.

Project Overview Report: Research on HoneyBadgerBFT Asynchronous Consensus Protocol
Overview:
This research aims to perform an in-depth study on the HoneyBadgerBFT asynchronous consensus protocol, with a focus on its designs and limitations. The primary goal is to contribute to the understanding of HoneyBadgerBFT's strengths and weaknesses while exploring its practicality. The research should possibly propose optimizations or new features. The research will involve analysis, simulations, and potentially the development of new practical implementations.
Project Introduction and Objectives:
The objective of this research is to investigate the HoneyBadgerBFT consensus protocol, considering both its theoretical foundation and its practical implications. The key research objective questions to address include:
What are the underlying principles and cryptographic techniques used in the HoneyBadgerBFT protocol?
How does HoneyBadgerBFT compare to other consensus algorithms in terms of performance, security, and decentralization?
What are the practical challenges in implementing and deploying HoneyBadgerBFT in real-world scenarios?
Can the protocol be optimized for scalability and efficiency while maintaining its Byzantine fault tolerance and asynchronous properties?
Are there potential applications beyond blockchain that can benefit from HoneyBadgerBFT's asynchronous design?
Resource Projections:
The research project is anticipated to require the following resources:
Time: Approximately 3 to 4 years for comprehensive research, experimentation, and thesis write-up.
Personnel: The primary researcher, advisors, and potential collaboration with industry leaders for discussions and review.
Computational Resources: Access to computing clusters for simulation experiments such as AWS, Azure, and Tor.
Literature: Readings of academic papers, research articles, and technical documentation related to consensus algorithms, cryptography, and the HoneyBadgerBFT.
Milestones and Deliverables:
Year 1:
Literature Review: Review of existing literature on asynchronous consensus algorithms, byzantine fault tolerance, and the HoneyBadgerBFT.
Theoretical Foundation: Develop a deep understanding of the cryptographic techniques and theoretical basis of the HoneyBadgerBFT.
Year 2:
Performance Analysis: Design simulations to compare the performance of HoneyBadgerBFT with other asynchronous consensus algorithms in terms of latency, throughput, and scalability.
Limitations and Challenges: Identify and analyze the limitations and challenges of the HoneyBadgerBFT from both theoretical and practical standpoint.
Year 3:
Optimizations: Investigate potential optimizations to enhance the efficiency and scalability of HoneyBadgerBFT without compromising security.
Real-World Viability: Explore practical implementations for deploying HoneyBadgerBFT in real-world scenarios.
Year 4:
Applications: Investigate potential applications beyond blockchain where HoneyBadgerBFT's privacy-preserving properties can be leveraged.
 Dissertation Preparation: Compile research findings, experiments, and insights into a comprehensive PhD Dissertation.

Scheduled Completions:
Literature Review and Theoretical Foundation: Year 1
Performance Analysis and Limitations Study: Year 2
Optimization Strategies and Real-World Viability: Year 3
Applications Exploration and Dissertation Preparation: Year 4
This research will contribute to the understanding of asynchronous consensus algorithms. It aims to provide insights into the HoneyBadgerBFT protocol and its potential impact on various distributed systems beyond blockchain. Through analysis, experimentation, and documentation, this research aims to advance the field of decentralized asynchronous consensus protocols.